## Collapsible Plan
COLLAPSIBLE PROJECT PLAN
Review week | 4 | Editable input: current project week
Native outline setup | In Excel, group rows 11:14, 16:19, and 21:24 using Data > Group > Rows
Metric | Value | Interpretation
Total tasks | 12 | Populated task IDs
Tasks needing action | 2 | Blocked or overdue unfinished tasks
Planned hours | 91 | Total planned effort (hours)
Hours remaining | 41 | Remaining effort, floored at zero per task
Task ID | Section / task | Owner | Status | Due week | Next action | Planned h | Actual h | Remaining h | Needs action
SECTION 1 | Discovery | Section summary — keep visible |  |  | Totals / action count → | 35 | 33 | 4 | 0
D-101 | Interview workbook users | Rin | Done | 1 | Archive notes | 8 | 8 | 0 | OK
D-102 | Map section structure | Jo | Done | 2 | Confirm headings | 12 | 14 | 0 | OK
D-103 | Define review fields | Malik | In progress | 4 | Approve status choices | 10 | 6 | 4 | OK
D-104 | Review accessibility | Rin | Done | 3 | Record keyboard notes | 5 | 5 | 0 | OK
SECTION 2 | Build | Section summary — keep visible |  |  | Totals / action count → | 34 | 12 | 22 | 2
B-201 | Prototype workbook | Malik | In progress | 3 | Resolve outline icon placement | 16 | 10 | 6 | Action
B-202 | Peer-test collapse and expand | Jo | Blocked | 4 | Confirm Mac Excel steps | 8 | 2 | 6 | Action
B-203 | Write usage notes | Rin | Not started | 5 | Draft update checklist | 6 | 0 | 6 | OK
B-204 | Protect formula cells | Jo | Not started | 4 | Review editable ranges | 4 | 0 | 4 | OK
SECTION 3 | Rollout | Section summary — keep visible |  |  | Totals / action count → | 22 | 7 | 15 | 0
R-301 | Apply groups in Excel | Jo | Done | 3 | Verify outline controls | 4 | 4 | 0 | OK
R-302 | Validate formulas after collapse | Malik | In progress | 4 | Compare expanded totals | 6 | 3 | 3 | OK
R-303 | Team handoff and next review | Rin | Not started | 5 | Schedule week-five review | 5 | 0 | 5 | OK
R-304 | Collect pilot feedback | Jo | Not started | 6 | Send feedback worksheet | 7 | 0 | 7 | OK