## Weekly Print Queue
WEEKLY WORK QUEUE — PRINT-READY REPORT
As of date | 46312 | Period start | 46306 | Period end | 46312 | Prepared by | Jordan Lee | Current sample print range | A1:J22
Total jobs | 12 | Open jobs | 8 | Complete jobs | 4 | Overdue open | 3 | Planned hours | 55
Actual hours | 26 | Actual minus planned (hours) | -29 | Urgent open | 4 | Due in period | 8 | Capacity limit (hours) | 60
Capacity status | Within capacity | Completion rate | 0.33333 | Exception note | Include overdue next actions | Remaining capacity | 5 | Next review date | 46319
PRINT WORKFLOW | Select A1:J22 for the sample; extend the final row as records are added.
INPUT GUIDE | Edit B2, D2, F2, H2, J5, J6 and A11:J30. Keep the summary formulas intact.
Job ID | Client / area | Work item | Owner | Status | Priority | Due date | Planned hours | Actual hours | Next action / note
WQ-101 | North Branch | Replace lobby signage | Avery | Complete | Medium | 46306 | 3 | 3 | Closed; photo archived
WQ-102 | Finance | Reconcile courier charges | Morgan | In progress | High | 46310 | 5 | 4 | Confirm final invoice
WQ-103 | Warehouse | Repair dock sensor | Casey | Blocked | Critical | 46311 | 8 | 1 | Waiting for vendor part
WQ-104 | HR | Update onboarding pack | Avery | Complete | Low | 46309 | 2 | 2 | Published version 4
WQ-105 | Retail East | Install price labels | Jordan | Planned | High | 46312 | 6 | 0 | Start after opening
WQ-106 | IT | Refresh loaner laptops | Morgan | In progress | Medium | 46313 | 4 | 2 | Image two remaining units
WQ-107 | Operations | Safety walk-through | Casey | Complete | High | 46307 | 7 | 8 | Follow-up logged
WQ-108 | Retail West | Audit back-room stock | Jordan | Planned | Low | 46315 | 3 | 0 | Confirm store access
WQ-109 | Facilities | Inspect roof leak | Avery | Blocked | High | 46308 | 5 | 1 | Awaiting access permit
WQ-110 | Legal | Archive signed contracts | Morgan | Complete | Medium | 46312 | 2 | 2 | Filed by year
WQ-111 | Customer Care | Revise escalation script | Casey | In progress | Medium | 46314 | 6 | 3 | Review with team lead
WQ-112 | Marketing | Pack event materials | Jordan | Planned | Low | 46316 | 4 | 0 | Print attendee badges