## PO Tracker
PURCHASE ORDER TRACKER
As-of date (yyyy-mm-dd) | 46327 | Currency | USD | Late grace days | 0 | Review cadence | Weekly
Controls | Edit B2, D2, and F2. Use one reporting currency throughout the sheet.
DECISION SUMMARY — CALCULATED
PO value excl. cancelled | 22501.44 | Open quantity | 5428 | Outstanding invoices | 3636 | Late receipts | 3 | Overdue actions | 1 | Exceptions requiring review | 7 | PO count | 10 | Fully received; status open | 0
Status | PO count | PO value | Outstanding invoice
Draft | 1 | 1047.6 | 0
Sent | 3 | 8551.8 | 0
Partially Received | 3 | 8649.6 | 3336
Received | 2 | 4252.44 | 300
Cancelled | 1 | 0 | 0
ENTRY GUIDE | Edit A15:P26 only. Q:T are calculated. Negative quantities or amounts are flagged and excluded from the affected calculation. UNUSED identifies prepared blank rows.
PO ID | Supplier | Category | Owner | Order Date | Promised Date | Status | Qty Ordered | Unit Price | Shipping / Other | Tax | Qty Received | Amount Invoiced | Amount Paid | Next Action | Action Due | PO Value | Open Qty | Invoice Outstanding | Priority Exception
PO-26041 | Atlas Components | Raw Materials | Maya Chen | 46290 | 46312 | Partially Received | 1000 | 2.4 | 180 | 0 | 600 | 1620 | 1200 | Confirm remaining 400 units | 46324 | 2580 | 400 | 420 | LATE RECEIPT
PO-26042 | Northstar Packaging | Packaging | Leon Brooks | 46300 | 46330 | Sent | 5000 | 0.18 | 95 | 0 | 0 | 0 | 0 | Confirm shipping date | 46325 | 995 | 5000 | 0 | ACTION OVERDUE
PO-26043 | Harbor Safety | PPE | Maya Chen | 46280 | 46310 | Received | 80 | 34.5 | 75 | 220.8 | 80 | 3055.8 | 3055.8 | Archive receipt documents | 46320 | 3055.8 | 0 | 0 | OK
PO-26044 | Brightline Office | Office Supplies | Priya Shah | 46315 | 46340 | Draft | 20 | 48.5 | 0 | 77.6 | 0 | 0 | 0 | Obtain purchase approval | 46328 | 1047.6 | 20 | 0 | OK
PO-26045 | Delta Machine Works | Maintenance | Leon Brooks | 46270 | 46300 | Partially Received | 4 | 1250 | 400 | 432 | 2 | 2916 | 0 | Escalate remaining backorder | 46322 | 5832 | 2 | 2916 | LATE RECEIPT
PO-26046 | Greenfield Lab | Quality | Priya Shah | 46295 | 46318 | Received | 12 | 89 | 40 | 88.64 | 12 | 1300 | 1000 | Resolve invoice variance | 46328 | 1196.64 | 0 | 300 | INVOICE > PO
PO-26047 | City Freight | Logistics | Maya Chen | 46305 | 46326 | Sent | 1 | 2200 | 0 | 0 | 0 | 0 | 0 | Confirm collection slot | 46326 | 2200 | 1 | 0 | LATE RECEIPT
PO-26048 | Everwell Catering | Services | Priya Shah | 46301 | 46308 | Cancelled | 1 | 850 | 0 | 0 | 0 | 0 | 0 | Record cancellation reason | 46309 | 0 | 0 | 0 | Cancelled
PO-26049 | Apex Fasteners | MRO | Leon Brooks | 46312 | 46332 | Partially Received | 300 | 0.65 | 25 | 17.6 | 350 | 237.6 | 237.6 | Resolve excess delivery | 46330 | 237.6 | 0 | 0 | OVER-RECEIVED
PO-26050 | Solstice IT | IT Equipment | Priya Shah | 46318 | 46345 | Sent | 5 | 980 | 60 | 396.8 | 0 | 5356.8 | 5500 | Request overpayment refund | 46329 | 5356.8 | 5 | 0 | OVERPAID
[16 empty] | 0 | 0 | 0 | UNUSED
[16 empty] | 0 | 0 | 0 | UNUSED